## Change Log
Cortez Framework — Change Tracking Log
WHBM PLCC Associate Cart Checkout bug fixes · Owner: Sivanesan · Shared codebase — log every add/modify here
# | Date | File / Class | Method / Location | Type of Change | What Changed (Description) | Reason / Bug Fixed | Related Test(s) | Status | Branch / Commit | Notes for Team
1 | 2026-07-06 | HomePage.java | handlePageLoading() (~line 1265) | Modified | Replaced action.findElement(...) hard-wait for the loading toast with driver.findElements(...) (plural) wrapped in try/catch; only waits for invisibility if the toast is actually present. | findElement threw TimeoutException when the '@role=alert' loading toast never rendered / faded too fast on QA2, cascading into ~40 downstream failures. This is a framework bug, not an app bug. | All PLCC/CBCC associate + account tests | In Progress |  | HIGHEST PRIORITY — fix this first. The dead 'if != null' guard never ran because findElement failed before it.
2 | 2026-07-06 | AccountsPage.java | myAccountLink @FindBy (~line 296) | Modified | Extended the account-link xpath to include the current QA2 attribute as an additional 'or' fallback alongside the existing data-test-id / data-qa selectors. | no such element: menu_header_account_my_account_link — QA2 build changed/removed the attribute, breaking navigation to My Account for all associate/loyalty PLCC flows. | verify_Associate_PLCC_Checkout_For_Tier3_Loyalty_User; Links_In_Account_Section_* | To Do |  | Confirm the exact new attribute by live DOM inspection on QA2 before committing.
3 | 2026-07-06 | AccountsPage.java | PLCC application form (continueAppcontent id) | Investigating | Investigating 30s timeout on By.id='continueAppcontent' in the PLCC credit-application step. | Genuine PLCC application failure — likely QA2 credit-decision service latency, changed iframe id, or stale test card data rather than a locator typo. | validate_PLCC_CreditCard_Application_Flow; CBCC application flows | To Do |  | May be an environment/data issue outside the framework. Coordinate with backend/QA2 owners.
4 | 2026-07-06 | WHBM_PLCC_Regression.xml | Suite config (thread-count) | Modified | Created a focused run: only the 9 AssociateCartCheckoutTest methods active, other 50 blocks commented out. Set thread-count to 1 while debugging. | Needed to run only the 22.22% PLCC_Associate group in isolation; serial execution keeps failures deterministic and screenshots matched to the right test. | 9 AssociateCartCheckoutTest methods | Done |  | Debug-only change. Revert thread-count to 30 and uncomment blocks before merging to shared suite.
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36

## Bug Status
PLCC_Associate_Cart_Checkout — Failure Tracker
2 passed / 7 failed (22.22%) · from WHBM_Report.html, Jun 26 2026 · update Status as fixes land
# | Failing Test Method | Root-Cause Signature | Owner | Status | Fix Ref (Change #) | Notes
1 | verify_Associate_User_Can_Apply_And_Remove_Coupon_In_Cart_And_Checkout | A: handlePageLoading toast wait | Sivanesan | To Do | #1 | Should clear once #1 lands
2 | verify_Associate_PLCC_Checkout_For_Tier3_Loyalty_User | A + B: toast wait + my_account_link | Sivanesan | To Do | #1, #2
3 | verify_Associate_CBCC_Checkout_For_Tier4_Loyalty_User | A + B: toast wait + my_account_link | Sivanesan | To Do | #1, #2
4 | validate_Associate_GC_Checkout_With_PLCC | A: toast wait (may hit C after) | Sivanesan | To Do | #1 | Re-check for C once A is fixed
5 | validate_Associate_GC_Checkout_With_CBCC | A: toast wait (may hit C after) | Sivanesan | To Do | #1 | Re-check for C once A is fixed
6 | verify_Successful_Associate_Checkout_With_PLCC_For_STH_BOPIS_GC | A + C: toast wait + continueAppcontent | Sivanesan | To Do | #1, #3 | Likely real PLCC form/env issue
7 | verify_Successful_Associate_Checkout_With_CBCC_For_STH_BOPIS_GC | A + C: toast wait + continueAppcontent | Sivanesan | To Do | #1, #3 | Likely real CBCC form/env issue
P | verify_CC_Checkout_For_Tier1_Loyalty_Associate_User | PASSING — plain CC, no PLCC path | - | Pass | - | Keep as regression baseline
P | verify_CC_Checkout_For_Tier2_Loyalty_Associate_User | PASSING — plain CC, no PLCC path | - | Pass | - | Keep as regression baseline

## How to use
How to use this log
Read me before editing
Purpose
This workbook tracks every change you make to the Cortez framework while fixing the PLCC Associate Cart Checkout failures, so teammates working on the same code know what you added or modified.
Change Log tab (main tab)
• Add one row per change. The # column auto-fills for blank rows.
• 'Type of Change' and 'Status' are dropdowns — click the cell to pick a value.
• Status colour-codes automatically: green = Done, amber = In Progress / Investigating, red = To Do / Blocked.
• Fill 'Branch / Commit' once you push, so anyone can trace the change back to git.
• Keep 'Notes for Team' honest about anything debug-only that must be reverted before merge (e.g. thread-count=1).
Bug Status tab
• The 7 failing + 2 passing tests of the 22.22% group. Update Status as each fix lands.
• 'Fix Ref' points back to the change number(s) in the Change Log that address that test.
Root-cause key
• A = handlePageLoading() toast wait throws on QA2 (framework bug, widest impact — fix first).
• B = my_account_link locator broken on QA2 (blocks account navigation).
• C = genuine PLCC/CBCC application-form failure (continueAppcontent etc.) — may be env/data, not framework.
Workflow tip
Log the change here the moment you make it, not at the end of the day — on a shared codebase a stale log causes merge surprises.